## Goal 1
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 1 - Increase the water supply and sanitation coverage
Accountable Manager – Addl. GM (S/E)
Objective 1.1 : |  | To achieve piped water supply coverage of 47.0 % (39% by the NWSDB) and piped sewerage coverage of 2.8 % of the total population of Sri Lanka by 2016
Strategy 1.1.1 - |  | Implementation of identified Water Supply & Sewerage projects
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.1 | Implement identified priority water supply & sewerage projects |  | • | Approved projects not yet commenced
|  |  | 1 | Rehabilitation & Augmentation of Labugama & Kalatuwawa Water Treatment Plants (Hungary) | 2012 - 2015 |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | 7302
|  |  | 2 | Kolonna and Balangoda Water Supply (Belgium) | 2012 - 2015 |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | 4458
|  |  | 3 | Greater Ratnapura Integrated Water Supply Project - Phase I (Spain) | 2013 - 2016 |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | 9928
|  |  | 4 | Increase of number of sewerage connections and access to safe sanitation in Colombo Area GPOBA (World Bank) | 2012 - 2015 |  |  | • • | Physical work commenced % physical progress | Addl. GM (Sewerage) | 1095
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.1 | Implement identified priority water supply & sewerage projects |  | • | Approved projects not yet commenced
|  |  | 5 | Badulla, Haliela & Ella integrated Water Supply (USA) | 2012 - 2016 |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | 8706
|  |  | 6 | Greater Dambulla Water Supply (Indian EXIM Bank) | 2012 - 2013 |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | 9593
|  |  | 7 | Augmentation of Colombo City Water Supply (ADB) |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P)
|  |  | 8 | Bandarawela, Diyatalawa & Haputale Integrated Water Supply (BOO/ BOOT basis) |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 9 | Kundasale Haragama Water Supply (BOO/ BOOT basis) |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | • | Water Supply Projects for which Expression of Interest (EOI) has been called; Not yet commenced
|  |  | 10 | Anuradhapura North Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 11 | Anuradhapura South Phase II Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 12 | Matara Water Supply - Stage IV |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 13 | Puttalam & Anamaduwa Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 14 | Makandura, Pannala & Kuliyapitiya Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.1 | Implement identified priority water supply & sewerage projects |  | • | Water Supply Projects which have been approved by the Standing Cabinet Appointed Review Committee (SCARC); not yet commenced.
|  |  | 15 | Augmentation of Mahiyanganaya Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 16 | Kiriibbanwewa Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 17 | Badalkumbura, Alupotha integrated Water Supply (Conditionally approved) |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 18 | Augmentation of Monaragala, Buttala integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 19 | Pathadumbara Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 20 | Greater Matale Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 21 | Kirama Katuwana Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 22 | Alawwa - Polgahawela Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.1 | Implement identified priority water supply & sewerage projects |  | • | Water Supply Projects identified for implementation funded by the China Development Bank; not yet commenced.
|  |  | 23 | Katana Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 24 | Mirigama, Kandalama Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 25 | Matugama, Agalawatta, Beruwala & Aluthgama Integrated Water Supply (Augmentation of Kalutara Integrated Water Supply - Stage III) |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 26 | Colombo City Distribution Expansion & Augmentation |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 27 | Greater Kurunegala Water Supply & Sewerage |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P,Sew) | N/A
|  |  | 28 | Dambadeniya Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 29 | Wadurupeenu Ella Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 30 | Middeniya Angunakolapelessa Integrated Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 31 | Rural Water Supply & Sanitation in Southern Province |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 32 | Nuwara Eliya District Rural Water Supply & Sanitaion |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 33 | Pathadumbara / Vavinna Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 34 | Thambuttegama Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 35 | Ruwanwella Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 36 | Hemmatagama Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
|  |  | 37 | Wadinagala Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 38 | Valachchanei Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 39 | Improvement of Rural Water Supply & Sanitation in Dry Zone (Kurunegala, Polonnaruwa & Matale districts) |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 40 | Mankulam Water Supply |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (P&P) | N/A
|  |  | 41 | Galle Sewerage |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (Sewerage) | N/A
|  |  | 42 | Maharagama/ Boralesgamuwa Sewerage |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (Sewerage) | N/A
|  |  | 43 | Hospital Sewerage Systems Improvement |  |  |  | • • | Physical work commenced % physical progress | Addl. GM (Sewerage) | N/A
Strategy 1.1.2 - |  | Complete on-going large scale water supply, sewerage and small & medium water supply projects
1.2 | Complete on-going large scale water supply, sewerage and small & medium water supply projects |  | • | Complete schemes under construction & commission | 2012 | - | 2016 | • | No. of projects completed | Addl. GM (WSP,S,W,N/C,S/E)
[8 empty] | • | % utilization of funds
|  |  | • | Establish service connections | On going |  |  | • | No of connections provided
1.3 | Construct new projects where funds are already available |  | • | Prepare implementation plans | [5 empty] | Addl. GMM (WSP,S,W,N/C,S/E)
|  |  | • | Award Tenders Implement construction plans | 2012 | - | 2016 | • | No. of schemes completed
|  |  | • | Implement construction plans
1.4 | Construct new projects where funds are not yet available |  | • | Secure funds for projects for which there is no budget allocation | [5 empty] | Addl. GM (P&P) Addl. GM (WSP, Sew., W, N/C, S/E)
|  |  | • | Prepare implementation plans | 2012 | - | 2016 | • | No. of schemes completed
|  |  | • | Award Tenders
|  |  | • | Implement construction plans
Strategy 1.1.3 - |  | Continue to identify new growth centres
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.5 | Identify new growth centers and develop project proposals |  | • | Identify reliable water sources |  |  |  | • | No. of projects developed | Addl. GM (Sew., P&P, W, N/C, S/E)
|  |  | • | Follow an integrated approach in the identification of water & sanitation projects; extend facilities or altanative means to population living near headworks | 2012 – 2016 on-going
|  |  | • | Prepare project proposals taking social, economic and environmental aspects into consideration |  |  |  | • | No. of population to be served
1.6 | Establish a criteria for developing water supply & sewerage projects on an integrated approach with other utilities |  | • | Prepare a Project Identification Criteria and agree criteria with other utilities | 2012 |  |  | • | Criteria established | Addl. GM (Sew., P&P)
|  |  | • | Apply developed criteria | 2013 on wards |  |  | • | No. of integrated projects planned
1.7 | Modify design criteria to extend facilities to communities living close to headworks |  | • | Use modified criteria in the design of projects | 2012 |  |  | • | Modified design criteria to be used | DGM (P & D)
Strategy 1.1.4 - |  | Ensure additional coverage during rehabilitation & augmentation of schemes
1.8 | Include additional coverage as far as possible during rehabilitation & augmentation of water supply and sewerage schemes |  | • | Prepare annual rehabilitation & augmentation plan by August of preceding year | 2012 - 2016 |  |  | • | Additional population served | Addl. GM (WSP,Sew.,W, N/C,S/E) | 600 p.a.
|  |  | • | Rehabilitate & augment water supply & sewerage schemes according to the plan
Strategy 1.1.5 - |  | Carry out campaigns for giving connections from completed water supply and sewerage projects
1.9 | Carry out campaigns for giving connections from completed projects |  | • | Use mass media |  |  |  | • | No. of campaigns carried out | Addl. GM (CS), Relevant PDD, RSC DGMs
|  |  | • | Use leaflets | 2012 onwards
|  |  | • | Carry out announcements/ campaigns
Strategy 1.1.6 - |  | Identify and implement Rain Water Harvesting and ground recharge programmes
1.1 | Identify urban and rural locations where rain water harvesting is possible & implement |  | • | Prepare annual rain water harvesting plan by August of preceding year | 2012 onwards |  |  | • | No. of Rain Water Harvesting Tanks constructed | RSC DGMs RWS Unit
|  |  | • | Seek funding for the programme
|  |  | • | Implement
|  |  | • | Carry out public awareness to promote the construction of Rain Water Harvesting Tanks |  |  |  | • | No. of Rain Water Harvesting Tanks constructed privately | Addl. GM (CS)
|  |  | • | Monitor incorporating rain water harvesting in new building plans approved by UDA and LA's |  |  |  | • | No. of building plans monitored | RSC DGMs
1.11 | Identify & Implement ground recharge where possible |  | • | Identify areas where ground recharge is possible | 2012 onwards |  |  | • | No. of projects implemented | RSC DGMs RWS Unit
|  |  | • | Publise the advantages of Ground Water Recharge
|  |  | • | Implement identified projects
Strategy 1.1.7 - |  | Adopt a mechanism to get public commitment to avail water supply and sewerage facilities
1.12 | Carry out pre construction surveys to get public commitment to use the facility |  | • | Establish consumer society to decide consumer commitments and to make the selection of new water served/ sewer network area more transparent | 2014 onwards |  |  | • | No. of consumer societies established | RSC DGMs
[8 empty] | • | No. of demand surveys carried out
1.13 | Use the funds allocated to meet the capital cost of water supply in-filling |  | • | Establish demand survey and carry out feasibility study | 2012 onwards |  |  | • | Funds allocated annualy | GM
Strategy 1.1.8 - |  | Introduce household purification to point sources (especially in unserved areas) to increase safe water coverage
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.14 | Public awareness and stake holder consultation in order to assess the need |  | • | Identify required public/ group | 2012 - 2016 |  |  | • | Identified needy group | RSC DGMs AGM (R&D) RWS Units
|  |  | • | Decide on appropriate household purification method |  |  |  | • | Identified appropriate methodology
|  |  | • | Conduct awareness programme in school and public places |  |  |  | • | Awareness programme conducted
|  |  | • | Publicity by leaflet
Objective 1.2 : |  | Prepare water safety plans to ensure high degree of water security with respect to quality and quantity for all water supply schemes
Strategy 1.2.1 - |  | Consider simple treatment plant options also to enhance quality and quantity
1.15 | Consider simple treatment plant modifications to enhance quality and quantity (applicable for water & sewerage) |  | • | Review design of treatment processes of the existing treatment plants for which water quality cannot meet the SL Standards or capacity enhancement is required | 2012 - 2016 |  |  | • | No. of treatment plants designed for improvement | RSC DGMs DGM (P&D) AGM (R&D)
[8 empty] | • | No. of treatment plants modified
Strategy 1.2.2 - |  | Establish framework for water source security and catchment protection
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.16 | Establish a Unit to handle water security issues at RSC's |  | • | Establish a Unit | 2012 |  |  | • | Unit established | Addl. GMM (P&P,Sew, W,N/C, S/E)
|  |  | • | Evaluate water source security issues | 2013 – 2016 |  |  | • | Policy guidelines prepared
|  |  | • | Prepare policy guidelines to address water security issues | 2013
1.17 | Ensure funds for water source security |  | • | Create awareness to policy makers and the public regarding the cost involved to obtain raw water (“Not Free”) | 2012 – 2016 |  |  | • | Awareness done | RSC DGMs Addl. GM (P&P)
|  |  | • | Secure funds for water source security by allocating a % of the TCE of new projects | 2013 onwards |  |  | • | Fund established (Amount)
1.18 | Identification and demarcation of catchment areas and implementing suitable protection programs |  | • | Identify and demarcate catchment areas to satisfy the required water demand | 2012 |  |  | • | No. of identified catchment areas | RSC DGMs
|  |  | • | Identify new water sources and demarcate the catchment areas |  |  |  | • | No. of new sources
|  |  | • | Implement catchment protection programmes | 2013-2016 |  |  | • | No. of catchment protection programmes being implemented
Strategy 1.2.3 - |  | Maintain storage capacities to ensure water security
1.19 | Identify potential feasible projects to ensure water security • Raising of existing dams • Cascade systems of reservoirs • Impounding reservoirs |  | • |  | 2012-2016 |  |  | • |  | RSC DGMs DGM (P&D)
1.2 | Develop a ground water development plan |  | • | Every RSC to develop its own ground water development plan | 2012 – 2016 |  |  | • | Ground water development plans developed | RSC DGMs DGM (P&D) AGM (R&D)
|  |  | • | Ground water recharging using rainwater on pilot scale. | 2012 onwards |  |  | • | Ground water recharge programmes launched
Strategy 1.2.4 - |  | Minimize saline water intrusion at water intakes
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.21 | Identify river intakes or boreholes where salinity problems exists |  | • | Identify river intakes or boreholes where salinity problems exist | 2012 |  |  | • | No. of intakes affected by salinity intrusion identified | DGM (NW, W-N, Prod., W-S, S, E)
1.22 | Make recommendation to the authorities concerned on the measures required to minimize salinity intrusion at river intakes/ bore holes |  | • | Forecast days of high tides during drought | 2012 |  |  | • | Recommendation made | Initial stage - DGM (NW, W-N, Prod., W-S, S, E) Secondary Stage - Addl. GM (P&P) DGM (P&D)
|  |  | • | Coordinate with other stakeholders to maintain minimum flow in the rivers by opening gates of upstream reservoirs on days of high tides. |  |  |  | • | No. of high tide days.
[8 empty] | • | No. of reserviors identified
|  |  | • | Identification of new reservoirs to store required water to be released during days of high tides. |  |  |  | • | No. of organizations agreed to implement.
[8 empty] | • | No of new reservoirs identified
1.23 | Formulate and Implement potential feasible projects to minimize salinity intrusion at water intakes considering • Floating intakes • Salinity Barriers • Any other feasible option |  | • | Promulate feasible projects | 2012 – 2016 |  |  | • | No. of projects formulated and implemented | Addl. GM (P&P)
|  |  | • | Implement projects
Strategy 1.2.5 - |  | Obtain policy guidance from the Government to allocate a given percentage of water from water bodies for piped water supply
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.24 | Seek to ensure a required water allocation from water bodies for piped WS |  | • | Prepare a policy paper justifying allocation of water for piped WS | 2012 |  |  | • | Policy paper produced | Addl. GM (P&P)
|  |  | • | Liaise with other national users on water allocation | Ongoing |  |  | • | Concurrence obtained
Strategy 1.2.6 - |  | Implement programmes to ensure that Water Quality is acceptable at water sources and intakes
1.25 | Develop and implement water quality surveillance and monitoring programs in water sources |  | • | Measurement of water quality (physical, chemical, bacteriological) monthly through out all the rivers use for water treatment plant at approximately 10 km interval. | 2012 - 2016 |  |  | • | Surveillance programme developed | RSC DGMs
[8 empty] | • | Programme in place
1.26 | Actively participate in divisional level co-ordination committee Meetings to improve protection of water sources (Establish committees if not existing) |  | • | Set up committees where they don’t exist | 2012 - 2016 |  |  | • | No. of existing committees | RSC DGMs
|  |  | • | Participate |  |  |  | • | No. of meetings participated/ represented
1.27 | Implement surveys on water bodies to identify pollution sources and types and to initiate appropriate actions |  | • | Develop procedure for surveys based on waer quality | 2012 - 2016 |  |  | • | Procedure developed | RSC DGMs
|  |  | • | Implement procedure |  |  |  | • | Procedure implemented
Strategy 1.2.7 - |  | Assist implementation of sanitation systems, with a view to minimize contamination of water bodies which are being used as sources for water supply schemes
Action |  |  | Sub Activities |  | Duration |  |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From |  | To
1.28 | Identify locations with unsafe septic tanks/ on-site sanitation which leads to contaminate water sources |  | • | Undertake field surveys to identify locations of contamination | 2012 - 2016 |  |  | • | No. of Locations identified | Addl. GM (Sew.) AGM (P&D - Sew.)
1.29 | Awareness on safe on-site sanitation |  | • | Preparation of a software programme to design septic tank, soakage pit and anaerobic filter |  |  |  | • | Software prepared to size septic tank/ soakage pit/ filter depending on number in household/ institution
|  |  | • | Distribution of the software among the Local Authorities and training them through a one day workshop at the Training Centre |  |  |  | • | Workshop held to train Local Authority staff
1.3 | Publishing the telephone numbers of the expertise group (RSC wise) to advise on sanitaion matters |  | • | Capacity Building of RSC staff by Training 2 officers from each RSC by P&D - Sewerage staff | 2012 |  |  | • | Training of staff of RSC's | Addl. GM (Sew.) AGM (P&D - Sew.)
|  |  | • | Publish contact persons to provide advice | 2012 |  |  | • | Contact details published | RSC DGMs
Strategy 1.2.8 - |  | Prepare water safety plans on pilot basis and expand it island wide
1.31 | Preparation of water safety plans for two treatment plants annually per RSC and implementation. Also identify other possible sources of contaminations in catchments of water bodies such as poultry, waste dumps, industrial discharges etc. |  | • | Study all possible contamination possibilities from the souce up to the customer's water tank | 2012 - 2016 |  |  | • | No. of water safety plans done | RSC DGMs AGM (RWS)
|  |  | • | Prepare safety measures to prevent pollution |  |  |  | • | No. of water safety plans being implemented
|  |  | • | Implement safety measures
|  |  | • | Undertake field visits and public consultation to identify sources of contaminations |  |  |  | • | No. of Locations identified
Note on B98: User: (Note to include a discription on this activity in the new CP book)

## Goal 2
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 2 - Improve Business Efficiency
Accountable Manager – Addl. GM (S)
Objective 2.1 : |  | To reduce NRW by 9.4 % in Colombo city during the period of 2012 – 2016 and achieve a 26% national average in 2016
Strategy 2.1.1 - |  | Continue emphasis on NRW reduction as an integral part of NWSDB operations
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.1 | Continue coordination framework for NRW reduction activities |  | • | Strengthen inspection procedures to detect illegal consumption | on-going |  | • | Procedure strengthened to detect illegal connections | RSC DGMs
[7 empty] | • | No. of illegal connections detected
Strategy 2.1.2 - |  | Implement short term and long term measures for the reduction of NRW especially in water supply systems such as Colombo
2.2 | Implement identified short term measures to reduce NRW |  | • | Introduce bulk meters at identified locations/ zoned metering for better NRW estimation | on-going |  | • | No. of bulk meters installed
|  |  | • | Strengthen leak detection unit and improve detection program |  |  | • | Leak detection unit strengthened
[7 empty] | • | Program improved | RSC DGMs
|  |  | • | Implement leak repair in transmission & distribution lines |  |  | • | Percentage leak repairs carried out
|  |  | • | Implement leak repair at headworks and raw water transmissions
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.3 | Implement identified long term measures to reduce NRW |  | • | NRW Reduction in Colombo City under Kaluganga WSP (JICA) | 2012 - 2013 |  | • | % physical progress | PD - Mrs.Chandra Perera | 10846
|  |  | • | Capacity Development Project for NRW Reduction in Colombo City (JICA) | 2012 |  | • | % progress | PD - Mr. S. G. G. Rajkumara | 200
|  |  | • | Greater Colombo Watet Supply Service Improving Project (ADB) |  |  | • | % physical progress | PD
2.4 | Propose recommendations to relevant authorities to amend NWSDB Act to recover/ collect loss of revenue |  | • | Seek approval for Act Amendment | 2012 |  | • | NWSDB Act amended | GM
|  |  | • | Levy loss of revenue to the NWSDB | 2012 - 2016 |  | • | Loss of revenue levied | RSC DGMs
2.5 | Establish proper pipe laying practice for house connections |  | • | Appoint a team for develop regulations and specifications |  |  | • | Team appointed | GM
|  |  | • | Develop regulations and specifications during implementation and pre qualification of goods and services for House Connections. | 2012 - 2016 |  | • | Regulations and specifications developed | Appointed team
|  |  | • | Introduce a Declaration System on quality control by the customer for house connection and pipe laying |  |  | • | A Declaration System Introduced | RSC DGMs
|  |  | • | Random Technical Inspectionsto be done by Senior Managers of the NWSDB. (Eg: 10 per month by every Manager and 5 per month by AGM or DGM) |  |  | • | No. of Random Technical Evaluations
|  |  | • | Usage of proper pipes and fittings and appropriate methodology (Eg: Use of Tapping Machines for House Connections) |  |  | • | Appropriate methodology used
|  |  | • | Monitoring of quality of goods and services of house connections through public participation |  |  | • | Monitored quality of goods and services through public participation
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.6 | Introduce endurance test results in tender specifications to monitor the quality of products used for house connections |  | • | Manufacture endurance test apparatus for water fittings used for house connections | 2012 - 2016 |  | • | No.of endurance test apparatus manufactured | DGM (Development)
|  |  | • | Appointe a commitee for preparation of Sri Lanka Standards (SLS) for manufactured endurance test apparatus for water fittings used for house connections. |  |  | • | No.of endurance test apparatus obtained SLS | GM
|  |  | • | Accredit manufactured endurance test apparatus by Sri Lanka Accreditation Board (SLAB). |  |  | • | No.of endurance test apparatus acctedied by SLAB | DGM (Development)
2.7 | Performance testing of water fittings and apparatus used for house connections |  | • | Establish Laboratories for testing of water fittings and apparatus in Colombo, Matara and Anuradhapura | 2012 - 2016 |  | • | No.of Laboratories Established | RSC DGMs
|  |  | • | Test performance of water fittings and apparatus during procurement stage |  |  | • | No.of water fittings and apparatus tested
|  |  | • | Test performance of random samples of water fittings and apparatus while in service |  |  | • | No.of water fittings and apparatus tested
2.8 | Design House Connections for various physical environmental situations; i. Rocky terrain; low depth ii. Hilly terrain; outside the embankment iii. Exposed to sun light iv. Using appropriate materials – eg: HDPE |  | • | Appoint a team of design engineers for the task | 2012 |  | • | Team appointed | GM
|  |  | • | Carry out designs |  |  | • | Designs completed | DGM(P&D)
|  |  | • | Issue instructions | 2013 |  | • | Instructions issued | DGM(P&D)
2.9 | Minimize Illegal Tapping |  | • | Promote public participation | 2012 - 2016 |  | • | No. of public participations | RSC DGMs
|  |  | • | Increase Fines (Seek approval for Act Amendment) |  |  | • | NWSDB Act amended | GM
|  |  | • | Improved rewarding system for information providers |  |  | • | No. of rewards | GM
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.9 | Minimize Illegal Tapping |  | • | Awareness campaign for school children | 2012 - 2016 |  | • | No. of awareness campaigns | RSC DGMs
|  |  | • | Initiate with National Institute of Education (NIE) to review the curriculum and introduce new educational materials on water conservation, case studies, projects for children, lessons to Teachers’ Guide, etc. |  |  | • | New educational materials introduced | Addl. GM(CS)
|  |  | • | Conduct training of teachers for the subject teachers and Guruupadeshaka on water sector activities and important messages to be absorbed by school children by Regional Support Centers. |  |  | • | Conducted training of teachers | RSC DGMs
Strategy 2.1.3 - |  | Continue to identify short term and long term measures for the reduction of NRW especially in water supply systems such as Colombo
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.1 | Continue to identify and implement short term and long term measures for the reduction of NRW especially in water supply systems such as Colombo |  | • | Strengthen inspection procedures to detect illegal consumption. |  |  | • | No. of illegal connections detected | Addl. GMM (W,N/C, S/E)
|  |  | • | Introduce bulk meters at identified locations/ zoned metering for better NRW estimation |  |  | • | No. of meters installed
|  |  | • | Strengthen leak detection unit and improve detection program | 2012 - 2016 |  | • | Leak detection unit strengthened | RSC DGMs
|  |  | • | Implement leak repair in transmission & distribution lines
|  |  | • | Implement leak repair at headworks and raw water transmissions |  |  | • | Percentage leak repairs carried out
|  |  | • | Develop defective meter replacement programmes |  |  | • | No. of defective meters replaced
|  |  | • | Rehabilitate of old, corroded & unserviceable pipes |  |  | • | Length of pipes replaced
|  |  | • | Defective valve refurbishment / replacement |  |  | • | No. of valves refurbished/ replaced
Strategy 2.1.4 - |  | Finance short term measures through internal sources and long term measures through external sources
2.11 | Finance short term measures through the Budget of the NWSDB Rehabilitation/ O&M |  | • | Estimate fund requirements for short term measures | 2012 - 2016 |  | • | fund requirements estimated | RSC DGMs
|  |  | • | Include request in Rehabilitaion/ O&M Budget |  |  | • | fund requirements budgeted
|  |  | • | Implement short term measures |  |  | • | Implement short term measures
2.12 | Finance long term measures through extenal sources |  | • | Package long term measures for NRW reduction and seek PAC, Board and Cabinet approval for foreign funding | 2012 - 2016 |  | • | Long term measures identified | RSC DGMs Addl. GM (P&P) AGM (P&S)
[7 empty] | • | Funding sought
Objective 2.2 : |  | To Minimize issue of ‘estimated bills’
Strategy 2.2.1 - |  | Convert un- metered connections to metered connections
Strategy 2.2.2 - |  | Replace defective meters
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.13 | Install meters to all un-metered connections |  | • | Identify un-metered connections and install meters | on-going |  | • | No of un-metered connections metered | RSC DGMs
2.14 | Replace defective meters |  | • | Identify defective meters |  |  | • | No of defective meters replaced | RSC DGMs
| Keep defective meters less than 1.5% |  | • | Implement a program to replace defective meters
2.15 | Evaluate performance of Meter Readers and provide training where required |  | • | Develop Training & Awareness programme for Meter Readers |  |  | • | No. of Training & Awareness programmes held for Meter Readers | DGM (Com) AGM (MD&T)
|  |  | • | Audit the meter readings |  |  | • | No. of Meter Readers recognized for competence in the NWSDB website
Strategy 2.2.3 - |  | Implement programmes and use new technology to obtain meter readings where the meter is not accessible/ readable
2.16 | Implement programmes and use new technology to obtain meter readings in the case of the meter being an accessible/ not readable |  | • | Introduce remotely readable meters for commercial and priority connections | 2012 - 2016 |  | • | No. of remotely readable meters installed | DGM (Com)
Strategy 2.2.4 - |  | Continue to analyse zero bills and estimated bills
2.17 | Analyse and monitor consecutive 3 months & 6 months estimated bills |  | • | Take corrective action to take actual readings | 2012 - 2016 |  | • | Total number of estimated bills | Addl.GMM (W,N/C, S/E) RSC DGMs
2.18 | Analyse and monitor consecutive 3 months & 6 months zero bills (Excluding disconnected premises) |  | • | Take appropriate action if water is used illegally | 2012 - 2016 |  | • | Total number of zero bills | Addl.GMM (W,N/C, S/E) RSC DGMs
|  |  | • | Replace or service meter if meter is defective or blocked
2.19 | Analyse and monitor number of Inactive Accounts |  | • | Identify the case and take action to recover the arrears, waive off or write off arrears and rectify the Account. | 2012 - 2016 |  | • | Total number of Inactive Accounts | Addl.GMM (W,N/C, S/E) RSC DGMs
2.2 | Identify and locate "cannot trace premises" and "cannot trace meters" |  | • | Take remedial action to read the meter or to rectify the problem | 2012 - 2016 |  | • | Total number of "cannot trace premises and meters" | Addl.GMM (W,N/C, S/E) RSC DGMs
Objective 2.3 : |  | To implement cost effective operations through increased Labour Productivity, Energy Efficiency and Treatment Process Efficiency
Strategy 2.3.1 - |  | Optimize the use of staff and other resources, outsource identified activities
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.21 | Introduce multi-skilled labour system where appropriate |  | • | Identify tasks that could be used by multi-skilled labour and assign | 2012 |  | • | Multi-skilled labour grades identified and implemented | RSC DGMs
|  |  | • | Develop guidelines, procedures and training necessary for implementation | 2013-2016 |  | • | Activities identified/ implemented |  | -
[7 empty] | • | Savings achieved
2.22 | Out source activities such as meter reading, security driver and janitorial services |  | • | Outsource identified activities | 2012 |  | • | Activities outsourced.
[7 empty] | • | Savings achieved
2.23 | Identify effective use of other resources (Land, office space, EDP equipment, vehicles etc.) |  | • | Seek appropriate approval for effective use | 2012-2016 |  | • | Depends on Actions | All sectional heads | -
[7 empty] | • | Savings achieved
Strategy 2.3.2 - |  | Continue the energy efficiency programme
Strategy 2.3.3 - |  | Formulate policy to use removable energy as much as possible and to select projects considering lowering power consumption
Strategy 2.3.4 - |  | Optimize operations in water and sewage treatment plants
2.24 | Undertake Energy Audits to identify inefficient pumps, plant and equipment under the guidelines set by Energy Saving Unit (ESU) |  | • | Develop Improvement Plan for inefficient pumps, plant and equipment using the results of Energy Audit and benchmarking | on-going |  | • | Improvement plan prepared | DGM (M&E) Head of ESU Managers (O&M) | To include in the Rehabilitation Budget
|  |  | • | Design pumps to be energy efficient
|  |  | • | Identify suitable funding sources
2.25 | Energy Conservation Project at Ambatale Water Treatment Plant (KfW) |  |  |  | 2012-2015 |  | • • | Physical work commenced % physical progress | Addl. GM (P&M)
2.25 | Adopt energy efficient methods |  | • | Train staff on energy efficient methods/ energy management | on-going |  | • | Staff trained | DGM (M&E) Head of ESU All Sectional Heads
|  |  | • | Use energy efficient methods in new schemes |  |  | • | Savings achieved
|  |  | • | Identify suitable funding sources
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.26 | Assess power requirements in project proposals |  | • | Check for high power requirements in project proposals at every stage | 2012 - 2016 |  | • | No. of project proposals in which power requirements were reviewed | RSC DGMs | -
2.27 | Check alternatives to reduce power consumption |  | • | Check for altenative arrangements, technologies to use methods of lower power consumption | 2012 - 2016 |  | • | No. of project proposals to reduce overall power consumption | RSC DGMs | -
2.28 | Check alternatives energy such as soler, wind, bio gas usage |  | • | Energy efficient lighting of buildings | 2012 |  | • | No. of buildings & plats using alternative energy | RSC DGMs
|  |  | • | Reduction of green house gas emission with low carbon foot print |  |  | • | Savings in electricity achieved through meter readings
2.29 | Optimize system operations for water supply & sewerage plants to perform efficiently |  | • | Effect system changes, modifications, improvements, etc. to optimize system operations | 2012 - 2016 |  | • | Savings achieved | RSC DGMs
Strategy 2.3.5 - |  | Introduce demand management for water supply and sewerage
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.3 | Carry out a survey on water/ sanitation needs |  | • | Feasibility study to contain demand survey results | 2012 - 2016 |  | • | Demand survey results included in feasibility reports | RSC DGMs | -
2.31 | Prepare appropriate water/ sanitation proposals |  | • | Feasibility reports to be prepared based on beneficiary needs | 2012 - 2016 |  | • | Feasibility reports prepared based on beneficiary needs | RSC DGMs | -
2.32 | Select/ Reject projects to based on the need |  | • | Feasibility reports to conclude on the type of water supply/ sanitaion facilities based on the need of beneficiaries | 2012 - 2016 |  | • | Type of water supply/ sanitation facilities proposed, based on community needs | RSC DGMs | -
Objective 2.4 : |  | To implement Research and Development on technology and process improvement for enhanced operational efficiency
Strategy 2.4.1 - |  | Conduct research & development on improving operational efficiency
Strategy 2.4.2 - |  | Conduct research on cost saving operations
Strategy 2.4.3 - |  | Conduct research on the possibility of using new technology and new business areas
2.33 | Continue framework for research studies within the institution |  | • | Hold Research Coordinating Committee Meetings | on-going |  | • | No. of Research Coordinating Committee Meetings held | Addl. GM (P&P) AGM (R&D) | -
|  |  | • | Allocate funds for Research & Development as per Board approval |  |  | • | Amount allocated for R&D | DGM (F) | -
2.34 | Continuation of research programmes Potential research areas are; |  | • | Prepare research outlines | on-going |  | • | Research outline prepared | Addl. GMM (Sew., P&P) AGM (R&D) | 200 p.a.
• | Water Safety measures (eg. Water Safety Plan, Point of use water treatment) |  | • | Approve research proposals by the Committee and allocate funds |  |  | • | Team appointed
• | Water Source Pollution studies |  | • | Appoint research team |  |  | • | Research completed
• | Advanced Treatment of Water & Wastewater
• | Water economy, scarcity, affordability and sustainability |  | • | Complete research assignments
• | Optimization of water supply schemes
• | Mitigation and Adaptation to climate change
2.35 | Identify possible new sources of income |  | • | Study feasible new business areas | 2012 |  | • | New business areas identified | Addl. GM ( P&P), AGM (R&D)
|  |  | • | Prepare feasibility studies | 2012 |  | • | appoint a team to identify new business areas |  | -
|  |  | • | Estimate net revenues that could be generated annually | 2012 |  | • | Feasibility studies developed
|  |  | • | Take initiatives to implement feasible new business areas | 2013 onwards |  | • | Annual revenue estimated
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.36 | Carry out awareness on promoting/ appliying research findings |  | • | Prepare publicity material | 2012 - 2016 |  | • | Awareness on applications of research results | Addl. GM (P&P), AGM (R&D) | -
|  |  | • | Disseminate
Strategy 2.4.4 - |  | Conduct research on climate pattern changing/ affecting forecasts
2.37 | Conduct research on climate pattern changing forecasts |  | • | Identify potential risks to water supply, sewerage schemes | 2012 - 2016 |  | • | No. of proposals prepared to avert effects of climate change | Addl. GM (Sew., P&P) AGM (R&D)
|  |  | • | Identify yield patterns in intakes |  |  | • | Data on the yield of Intakes
|  |  | • | Propose remedial actions |  |  | • | Data on the intakes abandoned
Strategy 2.4.5 - |  | Share research findings among other divisions for effective use of results within the NWSDB
2.38 | Findings to be presented quarterly |  | • | Hold quarterly meeting to present research findings | 2012 - 2016 |  | • | No. of meetings held to present research findings | Addl. GM (Sew., P&P), AGM (R&D)
Objective 2.5 : |  | To revise water and sewerage tariff annually to meet the cost of operation and maintenance and associated indirect expenses, debt service, depreciation and to generate reasonable surpluses
Strategy 2.5.1 - |  | Apply prepared tariff policy to cover full cost of O&M, associated indirect expenses, debt service, depreciation and generate reasonable surpluses
Strategy 2.5.2 - |  | Seek approval for the tariff formula
2.39 | Seek approval for adjusted tariff |  | • | Follow up with relevant authorities to get the tariff formula approved | 2012 |  |  | Tariff formula apporved | Addl. GM (P&P)
2.4 | Adjust water and sewerage tariff annually to represent full resultant cost of tariff formula |  | • | Appoint a team to analyze tariff adjustments annually according to tariff formula | 2012 - 2016 |  | • | Team appointed | Addl.GM (P&P, Sew.) DGM (Com.)
2.41 | Seek approval for adjusted tariff |  | • | Obtain approval of the Board |  |  | • | Board approval received
|  |  | • | Obtain Government approval |  |  | • | Government approval received
2.42 | Implement the approved tariff |  | • | Update the database of customers having sewerage connections |  |  | • | Approved tariff implemented
[7 empty] | • | Sewerage customer base updated
Strategy 2.5.3 - |  | Progressive financing of the Rehabilitation Plan
2.43 | Prepare a program for financing the rehabilitation plan |  | • | Assess rehabilitation budget requirements | 2012 - 2016 |  | • | Amount of surpluses to be spent on rehabilitation | Addl. GM (W, N/C, S/E) DGM (F) | 400 p.a
|  |  | • | Prepare programme to finance rehabilitation works
Strategy 2.5.4 - |  | Conduct a public education programme to explain the sanitary values of connecting to the central sewer systems
Strategy 2.5.5 - |  | Implement a procedure to attract households to connect to the central sewer system
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.44 | Undertake a public awareness program to educate households to connect to sewer systems |  | • | Appoint a team to prepare a public awareness program | 2012 |  | • | Team appointed | Addl. GM (Sewerage) DGM (Com) | 5 p.a.
|  |  | • | Prepare awareness programme incorporating by laws of LA's |  |  | • | Public awareness program implemented
2.45 | Provision of sewer connections |  | • | Provide sewer connections | 2012 - 2016 |  | • | % coverage with piped sewerage | Addl. GM (Sewerage) | 2 p.a.
|  |  | • | Carry out publicity campaigns for the public to secure sewere connections |  |  |  |  | Addl. GM (Sewerage)
Objective 2.6 : |  | To improve collection efficiency through the reduction of bill payment period and bad debts
Strategy 2.6.1 - |  | Establish new collection centers for customer convenience
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.46 | Continue to establish new collection centers |  | • | Identify locations and establish new collection centers considering geographical location and population density | 2012 - 2016 |  | • | New collection centers established | Provincial DGMs DGM (Com.)
2.47 | Improve payment facility through selected Banks /using credit cards/ using SMS/ through nominated agents |  | • | Assess feasibility to arrange payment using Credit Cards/ over the counter | 2012 - 2016 |  | • | Feasibility assessed | DGM ( Com)
|  |  | • | SMS notification & funds transfer |  |  | • | SMS notification/ payment system established
|  |  | • | Negotiate with banks on daily remittances or on line transfer |  |  | • | Negotiated with banks
Strategy 2.6.2 - |  | Appoint ‘Authorized Collection Agents’ and agree on daily remittances
2.48 | Continue to appoint authorized collection agents |  | • | Appoint a Committee to identify and establish credentials of suitable collection agents |  |  | • | Selected agents appointed | Provincial DGMs DGM (Com.)
|  |  | • | Agree on daily remittances
|  |  | • | Appoint selected agents
Strategy 2.6.3 - |  | Devise a procedure for the recovery of outstanding debts
2.49 | Reduce bad debts |  | • | Carry out age analysis |  |  | • | New procedure is in place to improve collections | Provincial DGMs DGM (Com) | -
|  |  | • | Update consumer accounts on daily basis | 2012 - 2016 |  | • | Improvement in collection ratio
|  |  | • | Send reminders and expedite recovery process
|  |  | • | Issue disconnection orders regularly
Objective 2.7 : |  | To economise on operating costs and to increase the efficiency of our services by outsourcing identified activities and if advantageous, through a subsidiary company owned by the NWSDB
Strategy 2.7.1 - |  | Prepare necessary polices and procedures
Strategy 2.7.2 - |  | Identify and agree on selected activities for outsourcing and those through the subsidiary company
Strategy 2.7.3 - |  | Provide an initial capital investment loan from the NWSDB to the subsidiary company
2.5 | Guidelines and support for formation of the subsidiary company |  | • | Appoint a team to prepare guidelines | 2012 onwards |  | • | Guidelines prepared and necessary approvals taken | Addl.GM (P&P) AGM (P&S) | -
2.51 | Identify outsourceable activities |  | • | Obtain approvals to carry out activities of the company |  |  | • | Identified activities to be outsourced
2.52 | Outsource agreed/ identified activities
2.53 | Outsource agreed identified activities to the subsidiary company |  | • | Appoint high level committee to identify activities to outsource |  |  | • | Activities identified to be outsourced
2.54 | Provide an initial capital investment loan from the NWSDB to the company |  | • | Arrange capital investment loan with necessary approvals. |  |  | • | Capital investment loan released.
Objective 2.8 : |  | Implement capital projects timely and within the estimated cost
Strategy 2.8.1 - |  | Streamline pre-construction planning in consultation with all possible stakeholders
Strategy 2.8.2 - |  | Streamline the procurement process of projects, coordinating among all stakeholders
Strategy 2.8.3 - |  | Proper reporting and monitoring of implementation constraints/ issues and progress of projects and taking timely actions in consultation with all possible stakeholders
Strategy 2.8.4 - |  | Amend NWSDB Act to suit for timely land acquisitions and for allowing necessary investigations
2.55 | Streamline pre-construction planning |  | • | Consult all possible stakeholders and carry out pre-construction planning | 2012 - 2016 |  | • | Procurement plans prepared | Addl. GM (WSP, Sew.) Project Directors | -
2.56 | Prepare and implement proper procurement plans |  | • | Consult all possible stakeholders and procure |  |  | • | Monitoring of physical progress with programme
2.57 | Monitor progress against programme |  | • | Report progress/ cost details accurately |  |  | • | Monitoring of cost of work done against TCE
2.58 | Take action to catch up lost time in projects |  | • | Plan to catch up lost time |  |  | • | Act amended
|  |  | • | Control cost escalations by staying within the original scope of work
2.59 | Amend NWSDB Act to permit entry to lands for investigations and to acquire lands without delays |  | • | Amend NWSDB Act to be emproved with rights for investigations after due notice and to acquire lats
Objective 2.9 : |  | Improve business efficiency through proper procurement planning
Strategy 2.9.1 - |  | Implement proper procurement planning
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.6 | Establish a database on end-user performance for goods and services, which could be useful for prequalification of manufacturers, suppliers and agents. (Identification of cause of failure, if any and feedback is very essential) |  | • | Establish the database | 2012 - 2016 |  | • | Database established | AGM (T & C)
|  |  | • | Update the database continuously |  |  | • | Date of last updation
|  |  | • | Evaluate manufacturers, suppliers, agents and contractors regularly using the end-user database results |  |  | • | No. of evaluation reports
2.61 | Pre qualify manufacturers, suppliers and service providers |  | • | Pre Qualification of manufacturers for; i. Sluice Valves, Stopcocks ii. Ball Float Valves iii. Air Valves iv. Pressure Reducing Valves (PRVs) v. Altitude Valves vi. Domestic Water Meters and Bulk Meters vii. DI pipes & fittings and Rubber gaskets viii. uPVC Tees ix. HDPE materials x. Ferrules xi. Clamp Saddles | 2012 - 2016 |  | • | No. of pre qualified manufactures for each item | AGM (T & C)
|  |  | • | Pre Qualification of manufacturers for chemicals |  |  | • | No. of pre qualified manufactures for each item
|  |  | • | Pre Qualification of contractors for services |  |  | • | No. of pre qualified manufactures for each item
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.62 | Introduce Sri Lanka Standards (SLS) for; i. Stopcocks ii. Ferrules iii. Angle Valves iv. Clamp Saddles v. Water Meters vi. Cisterns, Mixture Taps, Bidet Showers, Telephone Showers, etc |  | • | Provision in NWSDB Act – 1974 (Clause 90) to enforce the regulatory measures for water fittings used for house connections | 2012 |  | • | NWSDB act amended accordingly | GM
|  |  | • | Appoint a commitee for preparation of Sri Lanka Standards (SLS) for water fittings used for house connections. | 2012 -2013 |  | • | No of water fittings used for house connections, obtained SLS
|  |  | • | Preparation of SLS | 2013 -2014
|  |  | • | Seeking approval for Standers | 2014 -2015
2.63 | Campaigning for implementation of regulatory measures by the relevant authorities (such as NW&DB, Consumers’ Affairs Authority, SLSI, Sri Lanka Customs, etc.) to regulate the supply of goods by manufacturers, suppliers and dealers in order to have the quality products in the market. |  | • | Carry out campaigning | 2013 -2016 |  | • | No. of campaigns | Addl. GM (CS)
2.64 | Awareness campaigns for manufacturers, suppliers and dealers in the water industry on regulatory measures |  | • | Carry out awarness programmes | 2013 -2016 |  | • | No. of programmes | Addl. GM (CS)
2.65 | Advance Procurement Notice on prequalification of supplier agents and manufacturers for the products given in 2.54 |  | • | Issue Advance Procurement Notices | 2013 -2016 |  | • | No. of Advance Procurement Notices issued | AGM (T&C) & AGM (Supplies)
Objective 2.10 : |  | To develop, improve and implement a comprehensive Assets Management and Business Plans
Strategy 2.10.1 - |  | Continuously update the Assets Register with age analysis and valuation
Strategy 2.10.2 - |  | Continuously update and implement the Business plan
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
2.66 | Establish a Unit in every RSC Office for the management of assets |  | • |  | 2012 - 2016 |  | • | Assets management units established | Provincial DGMs
2.67 | Carry out Asset Management |  | • | Verify ownership of assets, regularize and assess the status |  |  | • | No. of schemes having Asset Management Plans |  | -
2.68 | Identify and regularise legal ownership of properties, plant & equipment |  | • |  |  |  | • | No. of scheme having clear ownership
2.69 | Replicate the Asset Management plan prepared by the ADB TA in every RSC |  | • | Review the existing Register of Assets | 2012 -2016 |  | • | Assets register reviewed
|  |  | • | Prepare asset register for all schemes |  |  | • | Asset register prepared
|  |  | • | Identify necessary investments to maintain assets |  |  | • | Investments identified
2.7 | Continuously update the Assets register with new assets/ obsolute items and transfer details to the central Assests Register prepared with the assistance of the Department of Valuation |  | • |  | 2012 - 2016 |  | • | Central Asset Register updated | Provincial DGMs DGM (F)
2.71 | Update a Business Plan and implement |  | • | Review the existing financial capacity | 2012 -2016 |  | • | SWOT analysis reviewed | Provincial DGMs DGM (F, Com.) AGM (P&S)
|  |  | • | Analysis and forecast of revenue and expenditure |  |  | • | Business Plan updated
|  |  | • | Analysis of existing tariff
|  |  | • | Analysis of loan repayment
|  |  | • | Identify alternative business areas |  |  | • | Investments identified
|  |  | • | Fix reasonable margin for operations
|  |  | • | Implement the business plan |  |  | • | Business Plan implemented

## Goal 3
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 3 - Improved services to customers and promptly attend to public complaints
Accountable Manager – Addl. GM (CS)
Objective 3.1 : |  | To take prompt action on customer complaints
Strategy 3.1.1 - |  | Continue to analyse main areas of customer complaints and formulate procedures to attend to such complaints within target times
Strategy 3.1.2 - |  | Train operational staff to improve customer relations
Strategy 3.1.3 - |  | Ensure that the Management Information System (MIS) will include information on public complaints/ requests, action taken on them and expenditure incurred
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.1 | Develop and implement procedures to attend to customer complaints |  | • | Categorize customer complaints | on-going |  | • | % Complaints resolved | DGM (Com) DGMM (Provinces)
|  |  | • | Assign the complaint to the responsible officer to coordinate action and to attend to it
|  |  | • | Communicate with the consumer
3.2 | Implement a training program for operational staff to improve customer relations |  | • | Review contents of training program & improve where necessary | on-going |  | • | No of officers trained on consumer relations | DGMM (Provinces) DGM (Com) AGM (MD&T)
|  |  | • | Train relevant officers
|  |  | • | Repeat the program annually
3.3 | Review & develop necessary changes to Management Information System on customer care |  | • | Review existing MIS on customer care | 2012 |  |  | Reviewed MIS on customer care | Addl. GM (CS)
|  |  | • | Develop necessary improvements to MIS on customer care & implement | 2012 - 2013 |  |  | No. of cases handled through MIS on customer care
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.4 | Implement Customer Complaints Handling System |  | • | Implement of CGS Module of the IT Solution throughout the Island. Extend CGS online with web based facility | on-going |  | • | No of provinces on implemented system | DGMM (Provinces) DGM (Com) DGM (IT)
|  |  | • | Call Centre Operations to be continued and facilities to be improved. |  |  | • | No of complaints resolved successfully
|  |  | • | Categorize customer complaints
|  |  | • | Develop MIS
|  |  | • | Assign the complaint to the responsible officer to coordinate action and to attend to it
3.5 | Monitoring of status of complaints |  | • | Monitoring of status of complaints assigned to responsible officers | on-going |  | • | No of actions taken successfully | DGM (Com)
|  |  | • | Communicate with the consumer
3.6 | Facilitate consumer to obtain a better customer service |  | • | Facilitate consumer to obtain a feedback for their complaints through SMS, E-mail, telephone or letter. | on-going |  | • | % of feedback from total complaints | DGM (Com)
|  |  | • | Cashier points kept opened during lunch hour |  |  | • | No of cashier points kept opened during lunch hour
|  |  | • | Computers, printers, and UPS units to be supplied and installed for Cashier Points |  |  | • | No of banks and supermarkets with water bill payment facilities in 24 hours and 365 days
|  |  | • | Make facilities available for payment of bills during evenings and holidays
Strategy 3.1.4 - |  | Preparation of procedures and guidelines to ensure customer satisfaction
Strategy 3.1.5 - |  | Customer complaints to be lodged at a location in close proximity
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.7 | Preparation of procedures and guideline to ensure customer satisfaction |  | • | Prepare guidelines | 2012 |  | • | No. of guidelines prepared | Addl. GM (CS)
3.8 | Provide facilities for customers to lodge their complaints at a location in close proximity to the water served area |  | • | Use of guidelines by relevant staff | 2013 - 2016 |  | • | Guidelines are being used
Strategy 3.1.6 - |  | Introduce sectional charter for every relevant section
3.9 | Introduce sectional charter for every relevant section |  | • | Develop sectional charter | 2012 |  | • | No. of sectional charter developed | Sectional Heads
|  |  | • | Obtain approval for sectional charter | 2012 |  | • | No. of sectional charter approved
|  |  | • | Implement | 2013 |  | • | No. of sectional charter Implemented
Objective 3.2 : |  | To improve public relations through the implementation of public awareness programme
Strategy 3.2.1 - |  | Prepare and implement public awareness programmes/ media campaigns raising funds from events (3-4 per year)
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.1 | Prepare programmes / media campaigns raising funds from events (3-4 per year) to overcome necessary expenses |  | • | Prepare programmes / media campaigns and carried out | 2012 |  | • | No. of programme carried out | Addl. GM (CS)
3.11 | Introduce Public and School Awareness Programmes to improve awareness on their responsibilities as water users |  | • | Continued Customer Awareness Programmes, review and develop the program periodically | on-going |  | • | No of Public and School awareness programmes developed, carried out and publicized | Addl. GM (CS)
|  |  | • | Ensure that the produced awareness programme will include the following;
|  |  | - | Pipe bursts and water leaks,
|  |  | - | Source protection
|  |  | - | Information on the management of water supply systems
|  |  | - | Conservation of treated water through promotion of alternative sources such as Rain Water
|  |  | - | Prevent pollution of water bodies and conservation of water for future generations
|  |  | - | Introduction of water saving / using devices for conservation
|  |  | - | Programme to avoid contamination within premises
|  |  | • | Identification of target groups and implementation of public awareness programmes to cover schools, religious institutions, State and Private institutions and marginalized groups |  |  | • | Identified target groups for awareness programme
|  |  | • | Awareness programmes publicized through media |  |  | • | No. of awareness programmes publicized
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.12 | Conduct awareness programmes on water/ sanitation to school children and teacher training colleges |  | • | Conduct awareness programmes on water/ sanitation to school children and teacher training colleges |  |  | • | No. of awareness programmes conducted | Addl. GM (CS)
|  |  | • | Review and develop the program periodically |  |  | • | No. of awareness programmes reviewed
3.13 | Conduct specific programmes on water quality, waste reduction and NRW reduction methodologies for institutions and commercial establishements |  | • | Conduct specific programmes on water quality, waste reduction and NRW reduction methodologies for institutions and commercial establishements |  |  | • | No. of awareness programmes conducted | Addl. GM (CS)
|  |  | • | Review and develop the program periodically |  |  | • | No. of awareness programmes reviewed
Strategy 3.2.2 - |  | Conduct training programmes for all employees dealing with customers
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.14 | Introduce training programmes for employees (including executive officers) dealing with customers |  | • |  |  |  | •
Objective 3.3 : |  | To improve and sustain quality of water supplied to National Standards (SLS 614 : 1983)
Strategy 3.3.1 - |  | Ensure effective functioning of all water treatment plants
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.15 | Supervision of treatment plants/ processes every six months by Engineer & Chemist to propose corrective actions |  | • | Prepare bi annual supervision schedule of all treatment plants and implement | on-going |  | • | No. of Plants supervised out of planned total | Addl. GMM (W, N/C, S/E)
|  |  | • | Take corrective action to improve quality |  |  | • | % of failed water samples
Strategy 3.3.2 - |  | Introduce appropriate water treatment processes
3.16 | Identify treatment plants producing poor water quality, which need improvements |  | • | Identify from monthly water quality report for action by the R&D section | on-going |  | • | % of samples failed with respect to water quality in each plant (duration is to be decided depending on the water quality parameter). | DGMM (Provinces) AGM (R&D) Chief of Laboratory Services
3.17 | Implement improvements at identified plants to full treatments |  | • | Identify locations where advanced treatment methodology is necessary to meet water quality Standards |  |  | • | Improvements to full treatment implemented
3.18 | Introduce advanced treatment methodologies where appropriate |  | • | Implement a pilot project with advanced treatment |  |  | • | Pilot project with advanced treatment implemented |  | AGM (R&D
Strategy 3.3.3 - |  | Enhance Laboratory facilities and continuous monitoring of water quality
Strategy 3.3.4 - |  | Carry out water quality surveillance programmes island-wide
Strategy 3.3.5 - |  | Control raw water pollution at intakes
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.19 | Provide necessary equipment and facilities to laboratories |  | • | Identify and provide additional equipment and facilities required for laboratories | on-going |  | • | Facilities provided | Addl. GMM (W, N/C, S/E) Chief of Laboratory Services
|  |  | • | Computerize laboratories where necessary | on-going
|  |  | • | Provide data transmission facility from the laboratories to the central laboratory and related functions | on-going
3.2 | Carry out water quality surveillance programme on schemes island-wide |  | • | Continue monitoring process of raw & treated water quality | on-going |  | • | % failure of water samples | Addl. GMM (W, N/C, S/E) Chief of Laboratory Services
|  |  | • | Coordinate with other stakeholders to monitor water quality of harvested rainwater, water taken from tube wells and protected dug wells randomly | on-going
|  |  | • | Improve & extend data base to include physical data, physical, chemical and bacteriological quality of raw & treated water on schemes island wide | on-going |  | • | Data base updated | Addl. GMM (W, N/C, S/E & P&P)
3.21 | Train & establish testing for parameters such as pesticides, arsenic, algae etc. and strengthen microbiology secti |  | • | Develop pesticides testing facility in central laboratory and in regional laboratory in Galle.??? | on-going |  |  | • Reporting on outcome | AGM (R&D) Chief of Laboratory Services
|  |  | • | Establish algae testing equipment in the central laboratory and in Provinces (GC,S&U,N&E,NW and C&S)???
Objective 3.4 : |  | To increase service levels with assured supply and adequate pressure
Strategy 3.4.1 - |  | System improvements to increase the supply level and residual pressure
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.22 | Rehabilitate and augment treatment plants, intakes, transmission and distribution systems to increase service level |  | • | Rehabilitate and augment treatment plants, intakes, transmission and distribution systems to increase service level | on-going |  | • | Increased supply hrs | Addl. GMM (W, N/C, S/E DGMM (Provinces)
|  |  | • | Scrape and reline old transmission and distribution lines
|  |  | • | Replace old mains to prevent sudden breakdown
Strategy 3.4.2 - |  | Implement preventive maintenance programmes
3.23 | Implement preventive maintenance progammes on a routine basis |  | • | Regularize the preventive maintenance program in RSC’s | on-going |  | • | Preventive maintenance program regularized | DGMM (Provinces)
Strategy 3.4.3 - |  | Attend to system breakdowns promptly
3.24 | Attend to system breakdowns promptly |  | • | Set time targets & attend to it quickly | on-going |  | • | System breakdowns unattended within target time | DGMM (Provinces)
Strategy 3.4.4 - |  | Develop O&M manuals for preventive maintenance
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.25 | Develop / update O&M Manuals for preventive maintenance |  | • | Review available material, update and implement O&M Manuals for preventive maintenance | on-going |  | • | No. of O&M Manuals in place & being implemented | DGMM (Provinces)
Strategy 3.4.5 - |  | Ensure water supply & sanitation facilities when a disaster occurs (Disaster Management)
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
3.26 | Make necessary arrangements for immediate water supply & sanitation facilities for the affected community. |  | • | Allocate Funds in the O&M Budget to meet expenses required in a disaster | 2013 - 2016 |  | • | Funds Allocated | DGM (F) | 100 m
|  |  | • | Establish a group to take required actions to provide water supply & sanitation facilities in a disaster, in every RSC | 2012 |  | • | Disaster relief groups established in RSC Western - Central Western - North Western - South Central Sabaragamuwa Uva Southern Eastern Northern North Western North Central | DGMM (Provinces)
|  |  | • | Train the group with clear understanding of the decision making authority in the event of a disaster | 2012 - 2016
|  |  | • | In the event of a disaster, seek assistance from a neighboring RSC if required.
|  |  | • | Make arrangements for Bowser Water Supply during a disaster
|  |  | • | Make arrangements for adequate sanitation facilities for refuge camps established by the Government Authorities during a disaster
3.27 | Make necessary arrangements to rehabilitate the damaged water supply & sanitation facilities |  | • | Identify damages in infrastructure | 2012 - 2016 |  | • | No. of projects implemented | DGMM (Provinces)
|  |  | • | Prevent water leakage/ sewer blockages
|  |  | • | Formulate projects including new projects for new settlement areas
|  |  | • | Arrange funds for formulated projects
|  |  | • | Implement projects for sustainable water supply & sanitation facilities

## Goal 4
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 4 -Promote Information and Communication Technology solutions as a catalyst for business growth
Accountable Manager – Addl. GM (WSP)
Objective 4.1 : |  | To upgrade in-house ICT Capacity
Strategy 4.1.1 - |  | Strengthen ICT Division and ICT facilities in other divisions
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
4.1 | Strengthen ICT Division and ICT facilities in other divisions |  | • | Prepare Road Map for IT Operations | 2012 |  | • | IT Road Map Finalized | Addl. GM (CS)/ DGM (IT)/ AGMM (IT)
|  |  | • | Identify the gaps in IT Cadre structure of the IT Division/ Other Divisions/ Region | 2012 |  | • | Proposed New cadre structure for IT Division | Addl. GM (CS)/ DGM (IT)
[7 empty] | • | Obtain approvals for the new cadre structure
|  |  | • | Fill the identified gaps in IT Cadre Structure of the IT Divison/ Other Divisions/ Regions | 2012 - 2013 |  | • | All vacancies of new cadre filled
|  |  | • | Asses the IT Infrastructure requirements (hardware, software, tools and connectivity solutions) against IT Road Map and identify the gaps. | 2012 - 2013 |  | • | Island wide IT Infrastructure deployment plan finalized
[7 empty] | • | Infrastructure Procurement Plan finalized
|  |  | • | Procure new requirements and upgrade the IT Infrastructure to suit the Road Map | 2012 - 2016 |  | • | Infrastructure identified are procured and deployed
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
Strategy 4.1.2 - |  | Establish Policies/ Guidelines
4.2 | Establish Polices/ Guidelines |  | • | Prepare a Comprehensive ICT Policy Document for the NWSDB | 2012 |  | • | ICT Policy Document Prepared | Addl. GM (CS)/ DGM (IT)/ AGMM(IT)
|  |  | • | Implement/Establish ICT Policy | 2013 |  | • | Circular issued | Addl. GM (CS)/ DGM (IT)
[7 empty] | • | Awareness Sessions Conducted
Strategy 4.1.3 - |  | Upgrade ICT Knowledge of Employees
4.3 | Upgrade ICT Knowledge of Employees |  | • | Identify Training Requirements | 2012 |  | • | Comprehensive Training Plan Prepared | DGM (IT)/ AGMM (IT)
|  |  | • | Conduct Training Programmes | 2012-2016 |  | • | Training Programmes conducted
Strategy 4.1.4 - |  | Deploy economical, authorized operating systems and application software (open source) in NWSDB’s computers
4.4 | Deploy economical authorized operating systems and application software (open source) in NWSDB’s computers |  | • | Evaluate and Identify Alternative Software available as Open Source Solutions for NWSDB needs | 2012 |  | • | Deployment Plan Prepared | DGM (IT)/ AGMM (IT)
|  |  | • | Identify Training/awareness Programmes required for use of alternative software packages | 2012 |  | • | Training Plan Finalized
|  |  | • | Carry out awareness/training sessions | 2013 - 2015 |  | • | Training/awareness sessions conducted
Objective 4.2 : |  | Implement Enterprise Resource Planning (ERP) Solutions
Strategy 4.2.1 - |  | Implement the ERP Solution at Head Office and Regions
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
4.5 | Implement ERP Solution at Head Office and Regions |  | • | Prepare a Implementation Plan | 2012 |  | • | Implementation Plan Finalized | DGM (IT)/ AGMM (IT)
|  |  | • | Implement the Solution at Head Office and Regions | 2012 - 2013 |  | • | Modules implemented at - Head Office - RSCs - Regional Offices - Regional Stores
Strategy 4.2.2 - |  | Carry out End user Training programmes and Administration Training Plan
4.6 | Carry out end user and administrator training programmes |  | • | Carry out end user training programmes | 2012-2016 |  | • | End user Training plan preapred | DGM (IT)/ AGMM (IT)
[7 empty] | • | Training Programms conducted for end users
|  |  | • | Carry out solution Administrator Training Programme | 2012-2016 |  | • | Administrator training plan prepared
[7 empty] | • | Training Programs conducted for solution administrators
Objective 4.3 : |  | To Establish Paper Optimized ICT Culture
Strategy 4.3.1 - |  | Develop Electronic Data Repository
4.7 | Establish Electronic Data Repository |  | • | Develop software solution for electronic data repository functions | 2012 |  | • | No of awareness programme | DGM (IT)/ AGMM (IT)
|  |  | • | Deploy the solution | 2012 |  | • | Software solution deployed
|  |  | • | Carry out end user training programmes | 2013-2014 |  | • | Training programmes conducted
Strategy 4.3.2 - |  | Develop ICT Solutions for Common Activities/Routine Work
4.8 | Develop ICT Solutions for Common Activities/Routine Work |  | • | Implement a solution for Document Management of Divisions | 2012 - 2014 |  | • | Solution implemented | DGM (IT)/ AGMM (IT)
|  |  | • | Implement a solution for CIPC approval procedure | 2012 - 2013 |  | • | Solution implemented
|  |  | • | Implement a solution for Vehicle DRC functions | 2013 - 2014 |  | • | Solution implemented
|  |  | • | Implement a solution for Circuit Bungalow Reservation | 2012 - 2013 |  | • | Solution implemented
|  |  | • | Implement a solution for IT Infrastructure Maintenance | 2012 - 2013 |  | • | Solution implemented
|  |  | • | Implement a solution for Tender Division | 2012 - 2013 |  | • | Solution implemented
|  |  | • | Implement a solution for budget preparation | 2012 - 2013 |  | • | Solution implemented
Objective 4.4 : |  | To establish online real time customer services
Strategy 4.4.1 - |  | Link to LGN (Lanka Government Network)
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
4.9 | Link to LGN |  | • | Liaise with ICTA to establish connectivity | 2012-2013 |  | • | Discussions with ICTA | DGM (IT)/ AGMM (IT)
|  |  | • | Establish connectivity |  |  | • | Hardware/Infrastructure Procured
[7 empty] | • | LGN Link established
Strategy 4.4.2 - |  | Develop interfaces with LankaGate Solution (Web Portal for Government Services, developed by ICTA)
4.1 | Develop interfaces with LankaGate Solution |  | • | Liaise with ICTA | 2012-2013 |  | • | Discussions with ICTA | DGM (IT)/ AGMM (IT)
|  |  | • | Develop interfaces through ICTA | 2012-2015 |  | • | No. of interfaces developed
Strategy 4.4.3 - |  | Develop in-house Solutions offering online customer services
4.11 | Improve Corporate Web Site |  | • | Carry out a requirement analysis | 2012-2013 |  | • | Requirement Documentation Prepared | DGM (IT)/ AGMM (IT)
|  |  | • | Modify the web site for new requirements | 2012-2014 |  | • | Improved web site launched
Strategy 4.4.4 - |  | Improve Corporate Web Site
4.12 | Develop in-house solutions offering online customer services |  | • | Improve the corporate web site to offer online services | 2012-2015 |  | • | Corporate web site improved to offer online services | DGM (IT)/ AGMM (IT)
|  |  | • | Adjust internal procedures to suit online services | 2014-2016 |  | • | Internal adjustments done
[7 empty] | • | Training programmes conducted
Objective 4.5 : |  | To improve the flow of management information (MIS) and coordination among divisions to enable planning and monitoring of activities
Strategy 4.5.1 - |  | Include information requirement of all divisions into the proposed MIS system
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
4.13 | Include MIS Requirements of all Divisions |  | • | Carry out a requirement analysis | 2012 |  | • | Requirements Specification Prepared | DGM (IT)/ AGMM (IT)
|  |  | • | Develop MIS system for the requirements | 2012-2013 |  | • | Solution developed and implemented
[7 empty] | • | Training/awareness Sessions Conducted
Strategy 4.5.2 - |  | Establish an Integrated Coordination System to all RSCs and Divisions of NWSDB
4.14 | Establish an Integrated Coordination System for all RSCs and Divisions of NWSDB |  | • | Assess Infrastructure Requirements | 2013 |  | • | Infrastructure Deployment Plan finalized | DGM (IT)/ AGMM (IT)
|  |  | • | Deploy Infrastructure Required for MIS | 2013 |  | • | Infrastructure procurement plan finalized
[7 empty] | • | Infrastructure deployed
|  |  | • | Carry out awareness sessions/training programmes for relevant officers | 2013-2016 |  | • | No of training prgrammes/awareness sessions conducted

## Goal 5
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 5 - Ensure greater accountability and transparency
Accountable Manager – Addl. GM (P&P)
Objective 5.1 : |  | To improve financial control to ensure proper management of funds
Strategy 5.1.1 - |  | Ensure compliance with established rules & regulations regarding accounting practices including government procurement guidelines
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
5.1 | Review existing financial procedures |  | • | Prepare Financial Manual
|  |  | • | Revise financial regulations, manuals and accounting practices | 2012 |  | • | Financial Regulations revised | DGM (F)
|  |  | • | Provide training to all staff on financial regulations | 2012 onwards |  | • | Training delivered
|  |  | • | Ensure compliance with accounting practices | 2012 onwards
Strategy 5.1.2 - |  | Introduce adequate internal checks & controls to weak areas & report non compliance for further improvements
5.2 | Undertake regular audit of revenue collections and payments |  | • | Prepare a plan for regular audits and execute | 2012 onwards |  | • | Audit plan prepared
[7 empty] | • | No. of audits conducted
5.3 | Introduce adequate internal checks and control in weak areas |  | • | Identify weak areas in financial administration
|  |  | • | Implement adequate checks and controls |  |  |  |  | DGM (IA) DGM (Com.)
|  |  | • | Take measures to introduce proper budget control
|  |  | • | Check compliance with financial regulations
Strategy 5.1.3 - |  | Implement stringent disciplinary action against misappropriation of funds
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
5.4 | Prepare/revise a Disciplinary Code to strengthen accountability |  | • | Appoint a team to prepare a Disciplinary Code, obtain the Board approval and execute the revised code | 2012 |  | • | Disciplinary Code revised and Board approval received | Addl. GM (CS)
5.5 | Carry out initial internal inquiry and take disciplinary action within three months. |  | • |  | 2012 onwards |  | • |  | Addl. GM (CS)
Strategy 5.1.4 - |  | Strengthen the Internal Audit Division with additional staff and logistics, including IA Units at RSCs
5.6 | Strengthen Internal Audit Department |  | • | Identify deficiencies of IA units | 2012 |  | • | Deficiencies identified | Addl.GM (CS) DGM (IA)
|  |  | • | Provide necessary support facilities | 2012-2016 |  | • | Facilities provided
|  |  | • | Appoint additional staff including multi disciplinary officials
Strategy 5.1.5 - |  | Introduce a system to reward employees who provide information on misappropriation of funds
5.7 | Encourage employees to produce information on misappropriation of funds |  | • | Work out & implement a rewarding program for the informants | 2012 - 2016 |  | • | Rewarding program implemented | Addl. GM (CS)
Objective 5.2 : |  | To achieve better performance of activities in Regional Support Centers (RSCs) with improved services
Strategy 5.2.1 - |  | Implementation of internal monitoring systems as well as technical and economic regulation
Strategy 5.2.2 - |  | Regional benchmarking leading to the collection, analysis and comparison of key provincial performance data
5.8 | Review KPIs of RSCs regularly, comparing each other and take action for necessary improvements |  | • | Review KPIs | on-going |  | • | Analysis and recognition of good performers | Addl. GM (P&P), DGM (CP)
5.9 | Setup benchmarks and action plans for achieving better performance |  | • | Set up benchmarks
Objective 5.3 : |  | To meet the debt service obligation of “Subsidiary Loan Agreements” with the Government
Strategy 5.3.1 - |  | Update the Annual Loan Capital Payable statement together with the Loan Interest Payable giving due dates
Strategy 5.3.2 - |  | Allocate cash flow to represent regular debt service payments, both capital and interest, on due dates
Strategy 5.3.3 - |  | Use loan repayment information for project planning process
Strategy 5.3.4 - |  | Make employees aware of debt and loan repayment commitments
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
5.1 | Update the Loan Repayable Schedule with due payment dates |  | • | Review the present loan repayment system | 2012 onwards |  | • | Loan repayment system reviewed | DGM (F)
|  |  | • | Prepare a comprehensive loan repayment schedule and update regularly |  |  | • | Comprehensive loan repayment schedule available

## Goal 6
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 6 - Promote Human Resource Development
Accountable Manager – Addl. GM (N/C)
Objective 6.1 : |  | To achieve performance excellence through change of attitude of employees and the Organizational Culture
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.1 | Appoint of committee to change employee attitude to work with dedication |  | • | Selection and appointing committee Addl. GMM - (N/C), (Sew.). DGMM - (P&A), (F), (Com.), (Audit), (CP). AGMM - (Admin), (Personnel), Specialist (WT). PO (Admin) Statistical Officer (CP) Regional Cordinators - MM(Support Service RSC) | 2012 - Mar. |  | • | Committee appointed | Special Committee for preparation of new CP for NWSDB
Strategy 6.1.1 - |  | Specific training programmes for attitude change
6.2 | Preperation of awareness/ presentation modules for change of attitude of employees |  | • | Identify existing culture in NWSDB | 2012 – June |  | • | Criteria developed | Appointed Committee
|  |  | • | Identify required changes to be made
|  |  | • | Develop a criteria/ modules for the attitude change
6.3 | Demonstration of the module and conducting a presentation to Chairman, Board Members, GM, Addl. GMM & DGMM for their observation and comments |  | • | Preparation of the presentation | 2012 - July |  | • | Presentation presented | Appointed Committee
6.4 | Implementation of the final programme for the staff on hierarchical order |  | • | Modify programmes according to comments by Audience under 6.3 | 2012 – Mid
|  |  | • | Identify budget and implemention system/ method |  |  | • | Programme implemented | Addl. GMM (Sew., CS) AGM (MPD)
|  |  | • | Conducting seminars including DGMM, AGMM and Other executive officers and other employees | 2012 – End |  |  |  | Appointed Committee
Strategy 6.1.2 - |  | Build up expertise employee groups for different subject areas
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.5 | Selecting specialized groups depending on the interest of the employees and recommendation of the superior |  | • | Deciding about expertise groups | 2012 - April |  | • | No. of expertise group established | Appointed committee
|  |  | • | Selection of members for the expertice group accoarding to allocated task
6.6 | Exposure of the selected expertise group to well run institutions and interaction with employees of simillar category |  | • | Selection relevant institutions for each group | 2012 – mid |  | • | Finalization of the selection | Expertise Group
|  |  | • | Preparation of a procedure to provide additional knowledge and skills if required
|  |  | • | Visiting the Institutions |  |  | • | Completion of visits | DGMM
6.7 | Completion of all studies up to the level required of expertism ( group members should be capable to handle any problem relevant to the category or group) |  | • | Study relevant activities up to level of required expertise using books & internet | 2012 – mid |  | • | Completion of relevant studies | DGM(CP)
6.8 | Prepare programmes to make aware NWSDB Management and staff on the important activities and relevant essential knowledge according to hierarchical order. |  | • | Creating multidisciplinary working environment | 2012 – mid onwards |  | • | No. of presentations done | Expertise Group
6.9 | Preparation of presentation according to hiarachial level |  | • | Use the expertise knowledge from the expertise groups if necessary Analysis of the feed back to evaluate the success of the programme | 2013 – mid onwards |  | • | No. of issues solved by using expertise knowledge
[7 empty] | • | No. of multidisiplinary Work categories such as treatment technician
[7 empty] | • | No. of employees with multiskill ability
Strategy 6.1.3 - |  | Convincing the employees of their importance (as an asset to the Board) for the development of the organisation
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.1 | Formulate and implement a culture changing programme for the NWSDB, emphasizing the importance of employees for development of organization |  | • | Defining an acceptable model for changing the organisational culture | 2012 |  | • | Submission of the modules | Appointed Committee
|  |  | • | Presenting to Chairman, GM, Addl. GM
6.11 | Making aware the employees of the acceptable model through seminars conducted for attitude change programmes in 6.4 |  |  |  | 2012 June | [5 empty] | 89127
6.12 | Monitor Organization Culture Change activities from top to bottom level |  | • | Monitor delays/ complaints | 2013 onwards |  | • | Outstanding reported delay/ complains/ investigation | DGM (P&A) and Divisional Heads
|  |  | • | Monitor no. of inquiries reduction
|  |  | • | Monitor Establishment of experties groups |  |  | • | No of expertise groups
6.13 | Evaluation of executive staff using external stake holders to assess employee performance |  | • | Prepare a relevant format for each executive officer of category for obtaining comments from external stake holders and maintaining a database about information received and forwarding it to the relevant officer without revealing the Identity of the person who comments. | 2012 |  | • | Preparation of format and database | Appointed Committee
|  |  | • | Preparation of the database | 2013 onwards
Strategy 6.1.4 - |  | Make aware the need for change of attitudes and inculcate a sense of ownership (Start a small change – each of us. Change begins with you and me)
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.14 | Exposure to well run institutions and interaction with employees of similar category (Necessary training on change management is included under the next objective - 6.2) |  | • | Selection of exemplary organizations for each category of employees and arrangement of visits to those organisations | 2012 mid |  | • | No. of visits to well run institutions (Heylies, CIC etc.) | Divisional Heads
6.15 | Prepare programme to make aware and interact with activities of other Divisions for the relevant staff |  | • | Visiting each division anually and learn about the activities carried out by relevent section and buidling up personal relationships. (DGMM of the sections should introduce the staff and staff should present their day today works to visiting group) Visit will be on 2nd or 3rd working days after 20th April, 1st and 2nd working days after 1st September or 1st and 2nd working days after 1st January next year | 2012 - mid onwards |  | • | No. of divisions visited
Strategy 6.1.5 - |  | Improve work processes in all Divisions according to internal charter
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.16 | Preparation of a summary of activities carried out by all divisions while identifying the relevant individuals for each actions |  | • | Collection of summary sheets for all the activities | 2013 onwards |  | • | Preparation of summary | All staff of supervising category (DGMM, AGM, Manager)
|  |  | • | Preparation of data base with the information |  |  |  |  | DGM (IT) EA, CO, etc.
|  |  | • | Providing information to the higher management for updating the job discription of relevent category |  |  |  |  | Relevent PO
6.17 | Preparation of a procedure manual indicating the methodology for carrying out each task found under 6.15 |  | • | Writing the methodology for carrying out each activity of the subordinate | 2013 onwards |  | • | Preparation of manuals | Supervising Officer
|  |  | • | Reviewing relevant section of the manual by the respective expertise group mentioned in strategy 2 |  |  |  |  | Relevant expertise group
6.18 | Improve work processes in all divisions |  | • | Identify suitable ethics and practices and publicise them among employees | 2012 – Stage I 2014 - onwards rest of this |  | • | Presentations by DGM’s on the effectiveness of this activity | DGM (CP) All divisions heads
Strategy 6.1.6 - |  | Motivate employees to work with dedication
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.19 | Internal promotions and relevant payments to be done in time (refer objective 2 for details) |  | • | Efficiency Bar exam, relevant test and interview for promotion to be held in due period | 2012 |  | • | Activities completed in due time | DGM (P&A)
|  |  | • | Salary increment made within a specified time
|  |  | • | Medical Claims to be paid within 10 days
6.2 | Rewarding to be done without applying (Gold Coin) |  | • | Prepare data base | 2012 |  | • | Database developed | DGM (P&A) DGM (IT)
|  |  | • | Inform employees in due period on entitlement of rewards sucha as Gold Coin for 25 years' service
6.21 | Introducing mobile service for handling problems of employees relevant to Personnel and Administration matters |  | • | Prepare programme for every RSC's | 2012 |  | • | No. of problems successfully attended and solved | DGM (P&A)
6.22 | Introducing counselling service where appropriate |  | • | Identify needy employees | 2012 |  | • | No. of solved problems | All sectional Heads - (Identify needs)
|  |  | • | Hiring qualified counselor |  |  |  |  | DGM (P&A) - (Facilitate)
6.23 | Educating the employees on the importance of the proper performance evaluation system to improve the NWSDB and thereby increase facilities for the employees |  | • | Conduct awarenss programmes | 2012 |  | • | No. of awareness programmes carried out | DGM (P&A) AGM (MTD)
6.24 | Implementing better performance appraisal system |  | • | Prepare a better evaluation system | 2012 |  | • | Eveluating the performance with the new system | DGM (P&A)
|  |  | • | Develop a database and Automatic evaluation systems using IT |  |  | • | Preparation of database | DGM (IT)
6.25 | Selection of proper interview system and panel (refer objective 2 for details) |  | • | Revise existing marking scheme | 2012 |  | • | Marking scheme revised | GM, Addl. GM (CS) DGM (P&A)
|  |  | • | Revise existing Interview method |  |  | • | Interview method revised
|  |  | • | Interview results to be finalized immediately after the interview |  |  | • | Whether interview results given on the same day
6.26 | Implementation of existing welfare schemes effectively |  | • | Conduct awareness programmes of existing welfare schemes | 2012 |  | • | No. of awareness programme conducted | Addl. GM (CS) DGM (P&A)
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.27 | Introducing new welfare schemes |  | • | Form a new welfare society for the entire organization | 2012 |  | • | Welfare societies formed | GM, Addl. GM (CS) DGM (P&A)
|  |  | • | Form sub society under DGM of RSCC with the autonomy
6.28 | Introduction of method to handle grievances of employees |  | • | Implement IT solution for grievances handlling for NWSDB employees as well | 2012 |  | • | IT solution implemented | DGM (IT)
6.29 | Implementation of a suitable motivation system by collecting relevant information from all categories of staff |  | • | Maintaining a suggestion box in all individual office premises | 2013 onwards |  | • | Establishment of suggestion box | DGM (P&A), RSC DGMM, Relevant Addl. GM
|  |  | • | Suggestions handover to the responsible officer who will carefully read and put it in to the suggestion box in front of the proposer or return it if not acceptable |  |  | • | No. of suggestions implemented
6.3 | Recognize aesthetic and extra talents of employees |  | • | Motivate employees to participate in aesthetic, religious and leisure activities | 2012 |  | • | No. of new members joined for recreational activities | All Sectional Heads
|  |  | • | Maintain a database on activities of employees
Strategy 6.1.7 - |  | Recognize contributions from professionals of all disciplines
6.31 | Addressing all the section under DGMM by Addl. GMM once in 6 months |  | • | Prepare a presentation covering important areas/ stressing the needs of all the professional activities (fitters, meter reader, labours, etc.) for development of NWSDB | 2012 |  | • | No. of sections visited | All Addl. GMM
6.32 | Addressing all the sections by DGMM (with help of selected employees if necessary) in Regions once in 06 months |  | • | Prepare presentation covering important areas/ stressing the needs of all the professional activities (Fitters, Meter Reader, Labourers, etc.) for the development of the NWSDB | 2012 |  | • | No. of sections visited | RSC DGMM
Strategy 6.1.8 - |  | Receive quality and performance awards from independent institutions
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.33 | Prepare quarterly progress reports on institutional development activities |  | • | Identify infrastructure development activities for progress monitoring | on-going |  | • | Progress reported | Addl. GMM (W,S/E,N/C) All sectional heads
6.34 | Apply for awards from independent agencies |  | • | Arrange seminars with assistance of productivity secretariat | 2012 |  | • | No. of seminars conducted
|  |  | • | Conduct seminars covering all sections
|  |  | • | Participate in programme conducted by productivity secretariat |  |  | • | Awards received
Strategy 6.1.9 - |  | Provide opportunities to all divisions to make use of available resources based on agreed criteria to achieve excellence
6.35 | Introduce e-mail, Internet and ADSL facilities for all Divisions to exchange information for decision making |  | • | Provide internet, e-mail, ADSL facilities to all Divisions specially OIC offices to communicate technical information | on-going |  | • | Communication through electronic media | Addl. GMM (W,S/E,N/C) All sectional heads
6.36 | Implement a technology sharing program with outside organizations |  | • | Technology sharing with identified organizations |  |  | • | Technology sharing
6.37 | Recognize employee contribution through participatory decision making (for better, faster and more effective work) |  | • | Motivate employees to make decisions at their level within their authority limits | 2012 |  | • | Successfulness of decisions
Objective 6.2 : |  | To prepare and implement a Human Resource Development (HRD) Plan
Strategy 6.2.1 - |  | Develop and implement well defined guidelines and procedures
Strategy 6.2.2 - |  | Develop a comprehensive database of employees with details of performance
Strategy 6.2.3 - |  | Prepare and issue a job description for all employees
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.38 | Develop and implement well defined guidelines and procedures for |  |  |  | 2012 |  | • | Preparation of guidelines | AGM (Personal)
• | Recruitment |  | • | Prepare a Master Plan for recruitment |  |  | • | Plan prepared
|  |  | • | Recruit them on time |  |  | • | No. of employees recruited on time
|  |  | • | Recruit the right person through a written test covering general knowledge, technical knowledge for executive staff and two interviews with two interview panels |  |  | • | Written test implemented
|  |  | • | Prepare a marking scheme considering extra curricular activities (sports, Sunday school attending, social works carried out, industrial activities (farming, producing, commodities, managing or working in small shops etc.) |  |  | • | Marking scheme revision
|  |  | • | Before calling for interview contact and finalize the marking scheme with the participation of interview pannel |  |  | • | No of interviews held and no of meetings for finalization of Marking Scheme
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
• | Recruitment |  | • | Clearly instruct the applicant on the document to be forwarded at the interview at least one week before the interview | 2012 |  | • | Whether this activity was done as appropriate | AGM (Personal)
|  |  | • | Make the applicants aware of the salary before the interview through advertisement or by letter when directly recruited through technical institutions |  |  | • | Whether this activity was done as appropriate
|  |  | • | Confirm the accuracy of relevant certificates for basic qualifications within a maximum three months |  |  | • | No. of occasions reported for delays of this activity.
• | Promotions |  | • | Fix dates for open cadre position in January and June every year | 2012 |  | • | Dates fixed | AGM (Admin)
|  |  | • | Preparation of a database to finalize the dates of retirement, leaving for long term fellowships etc. |  |  | • | Database prepared
|  |  | • | Conduct interviews before six months for closed cadre positions to train the person for the new task and provide suitable training
|  |  | • | Place the person under the present post holder for at least one month to confirm proper handing over of works
|  |  | • | Introduce a better evaluation system to give more wheightage at the interview
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
• | Succession |  | • | Preparation of a suitable training program for all the position by providing required training for carrying out the new task eg: AGMM -training on handling of financial and technical matters, administration and HR management Mangers - all O&M activities including NRW reduction, leak detection, distribution system maintenance, water treatment, budgeting, asset management and sewerage treatment etc. | 2012
• | Transfer |  | • | Implement present transfer system and appoint them accordingly | 2012
|  |  | • | Name the remote areas with shortage of suitable employees
|  |  | • | arrange special payments and benefits (transport facilities, quarters etc) for employees who go on duty to remote areas to compensate their burden for two years and re-appoint them with their agreement to a better place on completion of remote area service after two years if employee is willingly working in the remote area after two years, stop the special payment
6.39 | Establish an employees database |  | • |  | 2012 |  | • |  | DGM (IT)
6.4 | Review job description for all employees |  | • |  | 2012 |  | • |  | Addl. GM (Sew.)
Strategy 6.2.4 - |  | Revise job specification for all categories of employees timely, in line with improvement of the education system in the country
6.41 | Review academic qualifications from recognized institutions |  | • | Revise Selection Criteria for Recruitment once in five years considering above qualifications and finalyse before preparation of next corporate plan | 2012 - 2016 |  | •
Strategy 6.2.5 - |  | Develop and implement a Staff Training Plan that includes continuous training, hands-on experience and new technology & Management techniques
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.42 | Conduct Training Needs Assessment on the basis of HRD Strategy |  | • | Identify training needs | 2012 – 2016 |  | • | Comprehensive training programme prepared | Addl. GM (CS) DGM (P&A) AGM (MD&T)
|  |  | • | Give more emphasis for Internal Training using suitable personnel from NWSDB (Trainer should be changed if necessary considering the evaluation by participants)
|  |  | • | Identify training institutes and courses
6.43 | Formulate and implement a Staff Training Plan based on the Needs Assessment together with on-the-job training component |  | • | Prepare a training plan covering all the staff |  |  | • | Training programme implemented
6.44 | Develop manpower resources to meet future technological advancements |  | • | Appoint an official committee to support the AGM (MD&T) consisting of Specialists, AGM (R&D), DGM (Finance), DGM (P&A), DGM (Audit), DGM (M&E Services), Chief of Lab. Services, Chief Geologist, Chief Sociologist, etc.) Committee to be met once in three months (3rd working day of January, April, July, October) |  |  | • | appointing the committee | GM
6.45 | Develop impact evaluation system to evaluate the effectiveness of the training |  | • | Prepare a format to evaluate the impact |  |  | • | Preparation of format | AGM (MTD)
|  |  | • | Formats to be filled by Heads of the Sections |  |  |  |  | Heads of Divisions
Strategy 6.2.6 - |  | Maintain a safe, secure and enabling working environment
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
6.46 | Provide safety measures and ensure strict follow up of such measures to prevent accidents at work places |  | • | Circulate safety Standards | 2012 - 2016 |  | • | Strict follow up of safety measures | Addl. GM(CS) DGM (P&A)
|  |  | • | Implement industrial Standards and make aware the employee through safety engineer of the Labour Department
Strategy 6.2.7 - |  | Establish proper monitoring system
6.47 | Appointed committee to monitor all the activities |  | • | Committee should consist of all Addl. GMs and GM |  |  | •
|  |  | • | Meet once in three months to monitor the progress
|  |  | • | Invite two or three academics from a Sri Lankan University to participate in discussion as necessary

## Goal 7
CORPORATE PLAN 2012 – 2016
ACTION PLANS
Goal 7 - Facilitate safe drinking water supply and sanitation to rural and underserved communities
Accountable Manager – Addl. GM (W)
Objective 7.1 : |  | To reduce “unsafe” water supply by increasing safe water supply and sanitation coverage to rural and underserved communities through participatory planning
Strategy 7.1.1 - |  | Carry out water quality surveillance program in liaison with the Department of Health and other stake holders
Strategy 7.1.2 - |  | Include percentage of 5% from all water supply and sanitation projects implementing by NWS&DB for the rural sector and underserved communities
Strategy 7.1.3 - |  | Carry out awareness among rural and underserved communities on their health and hygienic status
Strategy 7.1.4 - |  | Provide safe drinking water supply and sanitation to rural and underserved communities by planning, design, construction and operation and maintenance of community water supply and sanitation facilities
Strategy 7.1.5 - |  | Provide alternative /including bottle water facilities for those who prone to health problems because of consuming unsafe water
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
7.1 | Carry out water quality surveillance program in liaison with the Department of Health and other stake holders |  | • | Implementation of WQS program for CBO |  |  |  |  | Addl. GMM (P&P ) DGM(RSCC) AGM (RWS)
|  |  | • | Strengthening laboratories of NWSDB to cater the demand of WQS program |  |  | • | Equipment provided
|  |  | • | Establishment of district water quality surveillance committee chaired by GA |  |  | • | Continuation of district WQS committee
|  |  | • | Water quality testing – Regulatory purposes Tested by NWSDB free of charge Sample to be sent by the MOH |  |  | • | No of samples checked
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
7.2 | Include 5% from all water supply and sanitation projects implemented by the NWSDB for rural sector development |  | • | Prepare guideline |  |  | • | Guideline implemented | Addl. GM (P&P) All PDs
|  |  | • | Implement the guideline |  |  | • | 5% included in proposals listed
|  |  | • | When the project proposals are submitted, the provision of 5% should be checked by the PAC |  |  | • | Allocation of 5% after signing project agreement
[7 empty] | • | Listing of projects from which 5% was allocated
7.3 | Identify needy rural and marginalized communities |  | • | Develop a criteria for the identification of needy rural and marginalized communities |  |  | • | Criteria developed for identification of needy communities | Addl. GMM (W, S/E & N/C) AGM (RWS) Chief Sociologist
|  |  | • | Identify needy communities and prioritize communities on need basis (Poorest of the poor should be addressed even if they do not demand owing to ignorance) |  |  | • | Rural and marginalized communities identified with prioritization
7.4 | Implement water supply and sanitation schemes in selected areas |  | • | Carry out awareness among communities to understand their needs with the consultation of the Ministry of Health |  |  | • | Community awareness carried out | Addl. GMM (W, S/E & N/C) AGM (RWS)
|  |  | • | Design and implement schemes on community participation basis |  |  | • | Schemes implemented with community participation
|  |  | • | Provide advisory services for sustained operation of CBO’s
|  |  | • | Project proposals for RWS to be prepared
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
7.5 | Ensure awareness on water related health problems; address by considering water requirement specially for drinking and cooking demand of rural areas. |  | • | Provide water from NWSDB as a browser supply to CBO and to CBO sell water to consumers for only drinking and cooking needs |  |  | • | Formed CBO with in this system and supply water by the NWSDB | Addl. GMM (P&P ) DGM(RSCC) AGM (RWS)
|  |  | • | Introduce house hold level rain water harvesting programs |  |  | • | Implemented programs in village level
|  |  | • | Introducing advanced treatment systems to CBO to fulfil their drinking and cooking needs |  |  | • | Implemented programs in village level and introduced new technologies
7.6 | Follow a participatory approach in planning, design, construction and operation and maintenance of community water supply and sanitation facilities |  | • | Necessary guidelines and manuals prepared |  |  | • | Guidelines and manuals prepared | Addl. GMM (P&P ) DGM(RSCC) AGM (RWS
|  |  | • | Follow up by district RWS units and issues should be addressed in PCC meetings and within the NWSDB Collaboration with stakeholders in national, district level and divisional level |  |  | • | Establishment of PCC meeting and continuation
[7 empty] | • | Establishment of collaborative meeting in national level and district level
Objective 7.2 : |  | To provide advisory services on best options
Strategy 7.2.1 - |  | Update and disseminate Standards, guidelines, norms, procedures and best practices by the NWSDB
Strategy 7.2.2 - |  | Implement public awareness programmes on the nature of support services available from RSCs on rural water supply and sanitation and hygiene education
Strategy 7.2.3 - |  | Ensure proper functioning of facilities for rural water supply and sanitation through established RWS Units in the RSCs for which budget allocation will be made available
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
7.7 | Prepare and update documents related to Best Practices including Standards, guidelines, norms and procedures |  | • | Preparation and updating of the documents |  |  | • | Documents prepared/ updated | AGM (RWS) Chief Sociologist
|  |  | • | Translation of documents into Sinhala and Tamil |  |  | • | Translated into Sinhala and Tamil
|  |  | • | Distribute documents to stakeholders (NGO’s, CBO’s, LA’s) and communities |  |  | • | Documents distributed
7.8 | Implement a public awareness program to explain the nature of services available from RSC’s |  | • | Prepare a public awareness program (using leaflets, media etc.) and implement the program |  |  | • | Programs implemented | AGM (RWS) Chief Sociologist
7.9 | Establish Units in RSC’s for rural water supply and sanitation; carry out ‘watch dog’ function |  | • | Prepare terms of reference for the Units and Identify necessary resources |  |  | • | Terms of reference prepared | AGM (RWS) Chief Sociologist
|  |  | • | Establish Units with necessary facilities |  |  | • | Resource requirement identified
|  |  | • | Check adherence to procedure among stakeholders |  |  | • | RWS Units in RSCs established
Objective 7.3 : |  | To ensure ‘value for money’ for the services provided to rural and marginalized communities
Strategy 7.3.1 - |  | Coordinate with stakeholders including Provincial Councils to provide water supply and sanitation facilities within the policy for rural water supply
Strategy 7.3.2 - |  | Make aware among communities to find most affordable options
Strategy 7.3.3 - |  | Encourage maximum contribution by the communities
Strategy 7.3.4 - |  | Ensure sustainability and proper functioning of community water supply and sanitation facilities
Strategy 7.3.5 - |  | Assist and recognize the role of CBOs and provide legal recognition
Action |  |  | Sub Activities |  | Duration |  | Verifiable Indicators |  | Responsibility | Cost (Rs. Mn)
[5 empty] | From | To
7.9 | Establish a mechanism for coordination with other stakeholders including Provincial Councils |  | • | Identify stakeholders involved and prepare a coordination mechanism |  |  | • | Stakeholders identified and coordination mechanism prepared | Addl. GMM (W, S/E & N/C) AGM (RWS)
|  |  | • | Liase with Provincial Councils for implementation |  |  | • | Provincial Councils’ concurrence obtained
7.1 | Make aware among communities to decide on affordable water supply and sanitation options |  | • | Prepare necessary material to educate rural and marginalized communities |  |  | • | Paper material prepared | Addl. GMM (W, S/E & N/C) AGM (RWS) Chief Sociologist
|  |  | • | Implement the awareness campaign through RSC’s (Making leaflets etc. available at district offices) |  |  | • | Communities educated